## WIP Calculator
Gross Mendelsohn
Work in Process Calculator
- input fields
Job No. | Job Name | Costs Incurred To-date | Total Estimated Costs | Percentage Complete | Total Contract Price | Estimated Total Gross Profit | GP % | Contract Revenue Earned To-date | Estimated Cost to Complete | Billed | Costs and Earnings in Excess of Billings | (Billings in Excess of Costs and Earnings)
|  | a | b | a/b=c | d | d-b |  | d*c=e | b-a=f | g | e-g=h | e-g=I
01 | example | 100000 | 150000 | 66.67% | 225000 | 75000 | 33.33% | 150000 | 50000 | 195000 | 0 | -45000
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0% |  | 0 |  | 0 | 0 |  | 0 | 0
|  | 100000 | 150000 |  | 225000 | 75000 | 33.33% | 150000 | 50000 | 195000 | 0 | -45000
If you have questions, call Marie Calabrese, CPA, at Gross Mendelsohn at 800.899.4623 or email her at mcalabrese@gma-cpa.com.
© 2023 Gross, Mendelsohn & Associates

## How to use this tool
Gross Mendelsohn
Work in Process Calculator Instructions
Costs Incurred To-Date – Enter actual costs applicable to the particular job incurred through date of desired financial report (typically month-end or year-end).
Total Contract Price – Enter total contract price including approved change orders.
Billed – Enter amount billed for the contract (including booked retainages) through date of desired financial report (see above).
Total Estimated Costs – Enter anticipated total costs at completion of job. This is the number that is most crucial and should be approved by lead project manager.
The rest will calculate automatically. The resultant net of costs and earnings in excess of billings (commonly known as "under billings") and billings in excess of costs and earnings (commonly known as "over billings") is the adjustment that should be made to contract revenue in your general ledger.
In the example contract, which reflected $195,000 in billings, a $45,000 debit to contract revenue (adjusting it to the earned to-date amount of $150,000 and a $45,000 credit to the billings in excess of costs and earnings liability account would be required to accurately report the contract in accordance with generally accepted accounting principles for fixed-price construction contracts).
If you have questions, call Marie Calabrese, CPA, at Gross Mendelsohn at 800.899.4623 or email her at mcalabrese@gma-cpa.com.
© 2023 Gross, Mendelsohn & Associates